## BookedHours
CITS3200 Project Billed Hours Record for Seb Each time you do some work on the project, note the week number, start and end date and hour, plus a brief description of the activity. At the end of each week send a copy of the sheet as it currently stands to your group's manager for recording on the group TimeSheet. Date in the form DD/MM/YY and time as XX:YY (24hr clock)
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours
| Date | Time | Date | Time
2 | 2025-07-27 | 16:10 | 2025-07-27 | 16:15 | Email Micheal Wise about client contact (how to do it) | 0.083333 | 0.083333 | 0.083333
2 | 2025-07-27 | 17:01 | 2025-07-27 | 18:50 | Created the git repo and added structure and base info to it | 1.8225 | 1.9058 | 1.8225
2 | 2025-07-27 | 18:10 | 2025-07-27 | 18:15 | Booked room for first meeting | 0.083333 | 1.9892 | 0.083333
2 | 2025-07-28 | 15:30 | 2025-07-28 | 15:45 | Send email to client asking for meeting/information | 0.25 | 2.2392 | 0.25
2 | 2025-07-28 | 15:51 | 2025-07-28 | 15:56 | Setup branch rules on the github repo | 0.083333 | 2.3225 | 0.083333
2 | 2025-07-29 | 12:10 | 2025-07-29 | 12:55 | First team meeting!! | 0.75 | 3.0725 | 0.75
2 | 2025-07-29 | 18:00 | 2025-07-29 | 18:10 | Send response email to cleint trying to organise meeting for monday morning | 0.16667 | 3.2392 | 0.16667
2 | 2025-07-29 | 18:10 | 2025-07-29 | 22:24 | Work on improving the github setup – added project/task board and issues, and switched to an organsiation instead of personal as that gives us better project management features | 4.2333 | 7.4725 | 4.2333
2 | 2025-08-01 | 10:20 | 2025-08-01 | 10:25 | Sent email to auditor asking to organise a meeting | 0.083333 | 7.5558 | 0.083333
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0